## Sheet1
Phase | no | feature | Time | price | Phase 1
1 | 1 | Pivot ON/OFF | 6 weeks |  | NO | PER | Task | Estimated time | unit
| 2 | Percent timer control |  |  | 1 | 100% | Designing system/Block diagram | 2 | day
| 3 | Direction control |  |  | 2 | 100% | Buying components | 2 | day
| 4 | Fertigation pump control |  |  | 3 | 100% | Schematic design | 3 | day
2 | 1 | Pump control |  |  | 4 | 100% | layout design | 5 | day
| 2 | Detect pivot position |  |  | 5 | 100% | PCB prototyping | 2 | day
| 3 | Detect running |  |  | 6 | 100% | Implementing software | 15 | day
| 4 | Detect pump status ON/OFF |  |  | 7 | 0% | Implementing with backend | 3 | day
| 5 | Water flow rate |  |  | 8 | 100% | Test | 5 | day
3 | 1 | Sprinkles pump control |  |  | 9 | 0% | Implementation in site | 3 | day
| 2 | End gun status | [5 empty] | 40 | day
| 3 | Stumble detection
All days is working days